## timeline
Publishing process - proposed timeline
Publishing process | Wks | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Est. cost
Planning & developing concept note | 3 to 4
Publications Committee concept note review | 2
Contracting & briefing writer(s) | 2 | [12 empty] | xxx
Writing & coordinating inputs | 12 to 16
Professional substantive editing | 2 | [12 empty] | xxx
Incorporating edits | 1
Internal review | 1
External peer review of final m/s | 2 to 4 | [12 empty] | (xxx)
Revising m/s following comments | 1
Professional copy-editing of revised m/s | 1 to 2
Reviewing m/s by Publications Committee | 2 to 3
Editorial Board review & sign-off | 2
Design/layout | 4 | [12 empty] | xxx
Professional proof-reading of laid-out PDF | 2 | [12 empty] | xxx
Incorporating edits in PDF (designer) | 1
PDF review (and additional review, if templates and standards were not met) & approval by Publications Officer | 1 to 2
Assigning ISBN (& DOI) by Publications Officer | 1
Cataloguing & digital release in lUCN Library database | 1 to 2
Printing & shipping | 2 to 3 | [12 empty] | xxx
Note: * Please include sufficient time for each step in the publishing process. This timeline serves as a guidance for the minimum amount of time needed to produce a publication. * Please make sure to plan enough time for possible translations, in particular if these need to be published simultaneously with the original version. Translation should only start AFTER the peer review tracking table of the post-peer review and copy-edited manuscript has been signed-off by the Editorial Board.