This paper has been prepared for IUCN’s World Commission on Protected Areas (WCPA) by Nigel Dudley and Sue Stolton of Equilibrium Research and Sarat Babu Gidda of the CBD Secretariat. Funding for the research has been provided by the governments of Finland, the Netherlands and Canada, UNEP – Spain Lifeweb Project, and Conservation International and the meeting in Jeju Island is supported by the government of the Republic of Korea and the IUCN Protected Areas Programme. Please send comments to Nigel Dudley: nigel@equilibriumresearch.com

The Future of the CBD Programme of Work on Protected Areas

PURPOSE AND CONTENT OF PAPER

This paper is intended to stimulate debate and offer some initial suggestions on new strategies and opportunities arising from the review of the Programme of Work on Protected Areas (PoWPA) at the Convention on Biological Diversity’s (CBD) 10th Conference of Parties (COP) in Japan in 2010.

The paper starts (pages 3 and 4) with a brief summary of the progress on implementation of the PoWPA to date. A more detailed summary of progress on each goal is given in Appendix 2. The paper then has a summary of the overarching ways and means to strengthen implementation (page 5 and 6).

The major section of the paper follows looking at opportunities for the development of the PoWPA post 2010 (pages 7 to 14). Four key issues are discussed: issues that need greater attention; strategies and action plans for strengthening implementation: target and timetable issues; and funding opportunities.

Three appendices are included: the first (pages 15 to 17) provides a brief overview of the challenges that have arisen in the implementation of the PoWPA to date and includes recommendations for future success (which are also discussed in the opportunities section above). Appendix 2 (pages 18 to 33), prepared by the CBD Secretariat, draws on the 65 fourth national reports prepared by Parties to the CBD to give an overview of implementation to date on all the PoWPA goals. The final appendix, 3, (pages 34 to 36) provides a summary of Summary of COP 9 Decision IX/18.

DEVELOPMENT OF PAPER

A meeting in Jeju Island, South Korea in September 2009 will review progress and discuss the future of PoWPA. The meeting responds to the COP9 Decision (Section A, Para. 24) inviting IUCN to further contribute to the process of PoWPA review leading to the COP10. Recommendations will feed into decisions COP 10. IUCN WCPA was asked by the CBD Secretariat (SCBD) to collaborate in drawing up proposals for enhanced action. It invites feedback from IUCN members and we expect the ideas to develop further.

After the international meeting in Jeju, a series of regional meetings will take place in India, South Korea, Côte d’Ivoire, Colombia and Germany, which will provide further input. A final set of analyses and recommendations will be produced during 2010 in time for the COP 10 in October 2010.

The draft paper has already been made available to several thousand people through regional networks and was prepared, in English, and French and Spanish versions were prepared with support from the IUCN Protected Areas Programme, to facilitate feedback. Circulation has included: all PoWPA focal points; all Friends of PoWPA representatives; all invitees to the global meeting in Jeju; the WCPA steering committee; other IUCN commissions; regional IUCN offices and through them to many regional contacts; within NGOs; and on a PoWPA supporters’ Facebook page and a website forum run by the SCBD. Around fifty comments have been received to date and analysed; these are reflected in the current version.

PROGRESS TO DATE IN IMPLEMENTING PoWPA

The CBD recognises protected areas as cornerstones of biodiversity conservation. The PoWPA is seen as the most successful CBD initiative and was also the first to set measurable targets so that progress can be monitored, although take up remains incomplete and variable (see summary table overleaf and a detailed discussion in Appendix 2).

PoWPA has helped to create many new protected areas e.g. in Latin America, West Africa, Madagascar, Eastern Europe, North Eurasia and the Pacific and has addressed threats and built capacity. It has generally been more effective with “technical” issues (e.g. gap analysis) than social targets (e.g. governance and participation) and further assessment of the implementation of the findings of planning and assessment processes will further determine the success of the PoWPA over the next few years. Progress has been slow in much of Africa and parts of Asia, and only partially integrated with existing initiatives in Europe, such as the European Union’s Natura 2000 network.

PoWPA applies to all countries although some developed country governments seem to assume that it is mainly applicable to developing countries. Several of the technical elements of PoWPA, including developing tools and methodologies, remain incomplete.

Long-term, sustainable financing of management continues to be a core, underlying problem and funding levels have fallen far behind the levels identified as necessary within PoWPA. However, some individual project funds have been available and not all these are being spent, suggesting that there are in some cases also weaknesses of organisation and ability to make best use of opportunities.

Progress has been best in areas and on issues where there are “champions”; individuals or institutions that take a lead and coordinate. Effectiveness also increases when many partners – governments, local communities, indigenous peoples, NGOs and donors – all work together. Where citizen awareness of the values of protected areas is high, implementation of the PoWPA is often in an advanced state.

The first phase of PoWPA ends in 2010 for land and 2012 for marine. Most of the Phase 1 targets are unlikely to be met, although the results summarised in this paper show clearly that there has been significant progress. Encouragingly, there appears to be recognition of the need for PoWPA and commitment to continue implementing PoWPA into the future.

Table 1: Global progress in achieving PoWPA goals

Key: ♦ very little progress; ♦♦ some progress; ♦♦♦ fair progress; ♦♦♦♦ good progress; ♦♦♦♦♦ excellent progress

| Goal | Target | Target progress |
| --- | --- | --- |
| 1.1 | To establish and strengthen national and regional systems of protected areas integrated into a global network as a contribution to globally agreed goals (by 2010 for terrestrial and 2012 for marine) | ♦♦♦♦ globally for terrestrial; ♦ for marine areas |
| 1.2 | By 2015, all protected areas and protected area systems are integrated into the wider land- and seascape, and relevant sectors, by applying the ecosystem approach and taking into account ecological connectivity / and the concept, where appropriate, of ecological networks | ♦♦ likely to be achieved provided more systematic effort are put in place in next five years |
| 1.3 | Establish and strengthen by 2010/2012 transboundary protected areas, other forms of collaboration between neighbouring protected areas across national boundaries and regional networks, to enhance the conservation and sustainable use of biological diversity, implementing the ecosystem approach, and improving international cooperation | ♦♦♦ could be achieved partially if current trends continue |
| 1.4 | All protected areas to have effective management in existence by 2012, using participatory and science-based site planning processes that incorporate clear biodiversity objectives, targets, management strategies and monitoring programmes, drawing upon existing methodologies and a long-term management plan with active stakeholder involvement. | ♦♦♦ likely to partially achieved; but effective implementation is poor |
| 1.5 | By 2008, effective mechanisms for identifying and preventing, and/or mitigating the negative impacts of key threats to protected areas are in place. | ♦♦♦ re threat identification but mitigation and prevention is poor |
| 2.1 &2.2 | 2.1: Establish mechanisms for the equitable sharing of both costs and benefits arising from the establishment and management of protected areas (by 2008); 2.2: Full and effective participation of indigenous and local communities, in full respect of their rights and recognition of their responsibilities, consistent with national law and applicable international obligations, and the participation of relevant stakeholders, in the management of existing, and the establishment and management of new protected areas (by 2008) | ♦♦ for both the targets in some areas; way behind meeting the targets at global level |
| 3.1 | By 2008 review and revise policies as appropriate, including use of social and economic valuation and incentives, to provide a supportive enabling environment for more effective establishment and management of protected areas and protected areas systems. | ♦♦♦ partially achieved at global level |
| 3.2 | By 2010, comprehensive capacity building programmes and initiatives are implemented to develop knowledge and skills at individual, community and institutional levels, and raise professional standards | ♦♦♦ partially achieved at global level |
| 3.3 | By 2010 the development, validation, and transfer of appropriate technologies and innovative approaches for the effective management of protected areas is substantially improved, taking into account decisions of the Conference of the Parties on technology transfer and cooperation | ♦♦♦ partially achieved at global level |
| 3.4 | Target: By 2008, sufficient financial, technical and other resources to meet the costs to effectively implement and manage national and regional systems of protected areas are secured, including both from national and international sources, particularly to support the needs of developing countries and countries with economies in transition and small island developing States. | ♦♦ but way behind meeting the target at global level |
| 3.5 | By 2008 public awareness, understanding and appreciation of the importance and benefits of protected areas is significantly increased | ♦♦♦♦ partially achieved at global level |
| 4.1 | By 2008, standards, criteria, and best practices for planning, selecting, establishing, managing and governance of national and regional systems of protected areas are developed and adopted | ♦♦♦ for developing standards, criteria and best practices but adopting them poor at global level |
| 4.2 | By 2010, frameworks for monitoring, evaluating and reporting protected areas management effectiveness at sites, national and regional systems, and transboundary protected area levels adopted and implemented by Parties | ♦♦♦ further assessments being carried out so could be partially achieved at global level |
| 4.3 | By 2010, national and regional systems are established to enable effective monitoring of protected-area coverage, status and trends at national, regional and global scales, and to assist in evaluating progress in meeting global biodiversity targets | ♦♦♦ for monitoring coverage and trends through WDPA, but monitoring status is poor |
| 4.4 | Scientific knowledge relevant to protected areas is further developed as a contribution to their establishment, effectiveness, and management. | ♦♦♦♦ good progress to date |

WAYS AND MEANS TO STRENGTHEN IMPLEMENTATION: BACKGROUND

Strengthening implementation of protected areas requires concerted effort throughout society, national, regional and international alliances and a strong enabling policy framework. Six key elements are required:

- Human and societal capacity

- Financial capital

- Coordination among multiple agencies and sectors

- Cooperation among key stakeholders at multiple levels

- National and regional-level commitment

- Communication at all levels

Capacity: A structured and systematic capacity building effort is required, focusing on the array of protected area themes and based on national and regional needs, with a coherent plan of action. This includes:

- Enabling a regional technical support network of professionals such as the IUCN-WCPA membership

- Leadership by national and international NGOs in developing and strengthening capacity-building

- The full engagement of indigenous peoples and local communities in these efforts

- The collaboration of university and training programs to incorporate key issues into their curricula

- The establishment and maintenance of learning resources and libraries, accessible by electronic media

- The establishment of a global network of capacity-building experts and initiatives to coordinate efforts

Capital: Bilateral and multilateral donor support represents a major proportion of financial resources available for protected areas in developing countries. However, these resources are insufficient at their current and projected future levels. Governments, donors, international NGOs and the private sector should seek opportunities to create synergies and partnerships for protected area finance, and approach the lack of funding through concerted efforts. In particular, they should develop a diversified portfolio of traditional and innovative approaches to meet funding gaps and to develop and compelling and economically-viable business plans. Such plans will require a full assessment of the costs and benefits of protected areas.

Co-ordination: In order to mainstream protected areas, there must be coordination among key institutions, agencies and sectors. To achieve such co-ordination, policy makers should ensure that:

- Natural resource agencies (e.g., forestry, wildlife, fisheries) work toward common goals and objectives

- Key sectors that rely on the benefits of protected areas (e.g., tourism, fisheries) are involved in planning

- There is coordination with key funding agencies, such as the GEF and bilateral aid agencies

- There is coordination among national focal points of international conventions

Finally, such coordination is greatly enhanced by a multi-stakeholder coordination committee, and by a single, designated focal point that is responsible for leading this committee.

Co-operation: Co-operation among the stakeholders who support protected areas is also critical in order to avoid duplication cooperation and deliver the most efficient and cost-effective support. This is particularly true among donor agencies, which often provide funding for the same activities within the same country at the same time, and among NGOs, who often provide overlapping services. Ideally, donors and NGOs will co-operate at international and regional levels, to ensure that their financial and technical support at national and local levels is well coordinated.

Commitment: Strong local, national and regional leadership is critical for effective implementation. At a local level, committed and motivated protected area managers can become catalysts in encouraging innovation and kindling the dynamic spirit needed for success. Individual countries can demonstrate their strong leadership by openly declaring and committing to ambitious protection goals (e.g., Madagascar, The Bahamas, Costa Rica and Palau). Examples of regional-level commitments, in which neighbouring countries develop regional ‘challenges’ include the Micronesian Challenge, the Caribbean Challenge; the Pan Amazon Challenge; the Dinaric Arc “Big Win”  initiative, and the Coral Triangle Initiative. Commitment to empower communities, facilitating secure land tenure and resource rights, recognition of community conservation initiatives and promoting implementation of diversified governance types is also very important.

Communication: There is a critical need for policy makers to communicate with all key stakeholders. Effective communication for protected areas includes:

- Establishing mechanisms for public involvement in protected area planning

- Ensuring broad public access to the outcomes of planning exercises, such as ecological gap analysis

- Reporting on the status of implementation

- Build a constituency of interest in protected areas (e.g. by ensuring positive experiences of people visiting protected areas), to help keep protected areas high on the political agenda

Governments can generate a stronger call to action by clearly communicating the importance of protected areas in addressing climate change issues; their contribution to the achievement of Millennium Development Goals and their broader ecological, economic, social and cultural benefits. Communication also incorporates collecting and managing information; monitoring and reporting the results of implementation.

# The Six Key Elements of Success

There is clear international policy incorporating these key elements (CoP 9 decision IX/18 – see summary in Appendix 3); and that policy should be translated into concrete actions on ground in a coherent and mutually supporting manner.

OPPORTUNITIES FOR PoWPA’S FUTURE

COP-10 provides a unique chance to address any current shortcomings or omissions, remove barriers to implementation and apply lessons learned, through COP decisions or even new targets. Because COP-10 will also address many other aspects of the CBD programme, it also provides a chance to integrate the PoWPA more closely with other CBD programmes. The paper therefore looks at:

( Issues that need greater attention

( Strategies and action plans for strengthening implementation

( Target and timetable issues

( Funding opportunities

Some key issues identified during the discussions within IUCN-WCPA have already been highlighted by the CBD, particularly in recommendations from the COP 9; where this is the case we indicate the relevant recommendation (see Summary of Decision IX/18 in Appendix). The role of the consultation here is less about identifying need and more to do with drawing explicit proposals for how signatory Parties to PoWPA and other interested Parties might respond.

The revision will take place in the context of a broader discussion about likely futures, looking at the values of protected areas, including their critical part to play in conserving biodiversity, to develop a stronger vision of their role in meeting forthcoming and emerging challenges.

( ISSUES THAT NEED GREATER ATTENTION

Analysis of country reports identifies the following key gaps in implementation, which should be emphasised at COP-10, through new commitments and funding. These include both issues that have emerged to greater prominence since the agreement of PoWPA in 2004 and elements of the existing PoWPA where delivery has been less satisfactory. In the list below, issues are ordered according to the most relevant target in PoWPA, no prioritisation is intended. Each issue included potential CBD responses and actions by partners: these are preliminary ideas for discussion.

- A major focus on marine protected areas (e.g. Activity 1.1.6) including high seas (Activity 1.3.2): targets for MPAs are not being met; a concerted global programme should therefore be initiated, in cooperation with IUCN-WCPA marine and all relevant agencies, stressing wider links to food security, ecosystem-based adaptation to climate change and human welfare. Currently within the CBD, MPAs are falling between two programmes - PoWPA and the Marine and Coastal Programme of Work. The latter, in practice, tends to focus on high seas protected areas and coastal protection is in consequence falling between the two programmes and being missed in terms of implementation. Opposition from fishing interests and some governments is also hampering progress; more use of IUCN protected area management categories IV-VI could help to address this.

Potential CBD responses: consider splitting the targets into two: for national MPA systems and for MPAs beyond national jurisdiction. Closer coordination is needed between PoWPA and the CBD Marine and Coastal Work Programme, including joint targets and agreed actions.

Actions for partners: WCPA Marine should have a key role in coordinating international responses to the marine components of PoWPA.

- Broadscale approaches to conservation (e.g. Activity 1.2; COP 9 Decision IX/18 – 4a) and 6c): including issues related to transboundary protected areas, connectivity, biological corridors and the integration of protected area networks into broader landscape and seascape approaches require more attention, particular in light of new pressures emerging from climate change. This has major implications for protected area system design. Further clarification is needed about how this might be reflected within the PoWPA.

Potential CBD responses: consider a request to Parties to map existing and potential areas that might fit into the category of “other conserved areas” – sustainably managed areas that support biodiversity, buffer zones, corridors etc – that could help to ensure the success of broadscale conservation strategies and to integrate these into national climate response strategies.

Actions for partners: WCPA and UNEP-WCMC could initiate a joint project to define “other conserved areas” and agree a way of recognising and recording these (existing ecoregional planning exercises might provide a useful basis of data for such exercises).

- The need for restoration (Activities 1.2.5 etc): restoration is becoming increasingly important inside and outside protected areas due to such factors as unsustainable development, invasive species and climate change. Restoration needs to address the challenge of maintaining connectivity in the wider landscape. It is important to monitor restoration over time and to link this with broader biological monitoring schemes. Currently many restoration efforts are project-based, which does not usually supply sufficient long-term resources to ensure success and more sustainable funding sources are needed for restoration efforts; various carbon credit schemes may help here.

Potential CBD responses: Consider convening a technical working group to address best practices of restoration in protected areas for purposes of protecting biodiversity

Actions for partners: WCPA and partners are developing technical guidance on restoration options in protected areas.

- Climate change (Activity 1.4.5 and COP 9 Decision IX/18): climate change was only briefly mentioned in PoWPA but has come to dominate the global conservation policy debate and also has implications for protected area management. The role of protected areas in carbon storage, mitigation through sequestration and ecologically-system adaptation needs to be better recognised and quantified, particularly with respect to the involvement of indigenous peoples’ and local community conserved areas and international discussions on avoiding deforestation and forest degradation within the Kyoto Protocol of the UN Framework Convention on Climate Change (UNFCCC) and follow-up instruments. These issues require more emphasis in PoWPA, through a recommended supplementary set of targets and activities, including potential actions that policy makers and managers can take.

In addition, PoWPA should be deployed as a major mitigation and adaptation tool by the UNFCCC including a joint implementation plan, and the role of protected areas systems in these responses should be emphasized in both climate and biodiversity discussions.

Potential CBD responses: consider development of a joint work programme with the UNFCCC’s Nairobi Work Programme focused on application of protected area systems as a tool for storage and sequestration of carbon and ecosystem-based adaptation to climate change.

Actions for partners: there is an urgent need for further research and field application on quantification of both mitigation and adaptation benefits: this could be an early output of IUCN’s PACT-2020 Initiative, working in collaboration with academic and NGO partners.

- A new initiative with indigenous peoples and local communities (Programme element 2; COP 9 Decision (IX/18) – 4c): the rights of indigenous peoples and local communities were well covered in PoWPA but delivery has been variable. There are good examples to learn lessons from, but still many cases of bad or inequitable practice; this is generally regarded as one of the least successful parts of PoWPA. There should be common cause between conservation and indigenous peoples, yet this is often lacking. Indeed at times protected areas become pawns in a broader dialogue addressing greater objectives such as land claims and restitution of past wrongs. Emphasis on building partnerships is needed, both generally around protected area values and specifically with respect to potential climate finance. This will require a concerted effort by governments, indigenous peoples and local community representatives and both conservation and development NGOs leading up to COP-10, including development of a realistic action plan and identification of sufficient resources to facilitate necessary meetings, research and consultation. These issues also require stronger leadership from international bodies in drawing attention to cases where human rights infringements are taking place.

Potential CBD responses: consider identification of a mechanism to allow the identification of national PoWPA focal points for indigenous peoples and local communities, alongside government PoWPA focal points, to collaborate on implementation of the PoWPA.

Actions for partners: WCPA should consider creation of a joint task force with CEESP, through TILCEPA, and in cooperation with supportive governments, to develop relevant technical guidance, best practice and capacity building related to objective 2 of the PoWPA.

- Promoting the full suite of protected area governance types (Activity 2.1.2; COP 9 Decision (IX/18) – 6.a, b and d): most Parties continue to give more emphasis to state-run protected areas and a wider vision has yet to manifest especially for indigenous and community conserved areas and private reserves and for the potential of co-management; although there are encouraging developments. The relationship between different governance types requires more attention and choices should be strategic and tailored to local conditions. The question of good governance is as important as the type of governance and should be reflected into monitoring and assessment systems.

Potential CBD responses: Consider an additional target for state parties to have assessed governance types of protected areas in the country and reported to the WDPA by 2015.

Actions for partners: responses should be a component of general responses to objective 2 above

- Wider services from protected areas (Activities 3.1.9; 4.4.2): the values of protected areas are better understood than when PoWPA was agreed and there is a need to build on the CBD’s technical report of 2008 to define specific targets and actions to optimise these benefits. Important additional values identified in the Millennium Ecosystem Assessment include for example a range of ecosystem services (e.g. soil stabilisation, water supply and purity, disaster mitigation); provision of food and materials (e.g. wild foods, agrobiodiversity, medicinal plants) and social and cultural values (e.g. sacred natural sites, places for recreation and historically important landscapes). Recognition of and management for such values can reduce internal tensions, both with respect to the protected area and more generally within the landscape. Integration into PoWPA requires efforts not only under the two activities above but also e.g. in assessment, governance, etc. However, there is currently no standardised guidance or methodology to measure costs and benefits of protected areas and how these are distributed, which means that discussion about who gains or loses from protected area formation is often based on hearsay.

Potential CBD responses: consider requesting a report-back from signatory governments on wider services from protected areas as part of the next national report on PoWPA.

Actions for partners: to support this, WCPA should work with NGO and government partners to agree a standard typology of benefits and associated tools for their measurement in/around protected areas. WCPA should also with urgency coordinate efforts to develop, field test and disseminate an agreed framework for carrying out cost-benefit analysis of protected area benefits with a suggested target date for completion of 2012.

- Monitoring and reporting (Target 4.2; COP 9 Decision (IX/18) 5.b.iv): existing reporting frameworks do not look at accountability or progress against specific targets. This could be addressed by developing a reporting framework for adoption at COP-10, which would need to be presented within the framework of a set of standard indicators at global level. It would require clear guidance about the reporting process (for example including those responsible for protected area management). Such reporting needs to be based on effective monitoring systems, such as those focused on maintaining the WDPA. The CBD PoWPA could also draw on some existing reporting frameworks, e.g. the database on transboundary protected areas and the global study on management effectiveness of protected areas, both maintained by UNEP-WCMC, and adopt these as official reporting tools for PoWPA implementation. Further methodological work is needed on some aspects of monitoring, including in particular monitoring of the biodiversity outcomes of protected areas (see COP 9 Decision (IX/18) – 4b), monitoring of governance quality and integration of ancestral knowledge into monitoring systems. Monitoring should also recognise progress towards reaching targets, as well as actual achievements to encourage those countries who are implementing the PoWPA from a low baseline.

Potential CBD responses: consider recognising the global study on management effectiveness and the WDPA data field related to effectiveness, as official reporting formats for the PoWPA

Actions for partners: WCPA and SSC should develop a database and methodology for more accurate monitoring of biodiversity outcomes within protected areas

- Emphasis on effective management and good governance (Target 4.2 and others): while progress has been made on assessment and capacity building, there has been less success in applying results to adaptive management; too many assessments are completed and the results never implemented. (The same is true for many management plans.) Greater efforts are therefore needed on both synthesis and learning lessons from assessment. Efforts are needed to encourage national adoption and possibly to develop regionally-specific assessment systems. An additional issue relates to protected areas in conflict situations: the inclusion of ecologists and protected area experts in teams from bodies such as the UN High Commission for Refugees and other relief agencies might help to reduce this problem. Protected areas also need to maintain their focus on protecting biodiversity. Particular attention is needed on economically valuable species in protected areas; many of these are declining dramatically due to poaching pressure, particularly in Asia and also in Africa and Latin America. New strategies, including stronger law enforcement, are urgently required in these cases.

Potential CBD responses: request signatory governments that report back on management effectiveness assessments (activity 4.2.2) to in addition report back on what this means in terms of management changes (activity 4.2.4), for example, incorporating findings of management effectiveness assessments into business plans so that the actual costs of improvements can be identified and follow-up actions and investments timetabled to enable better monitoring of responses.

Actions for partners: UNEP-WCMC and WCPA to continue to develop and populate the global database on management effectiveness studies.

( STRATEGIES FOR STRENGTHENING IMPLEMENTATION

Focusing on better PoWPA implementation, particularly through the availability of increased and more secure funding; currently funding is 30-40 per cent of estimated requirements at global levels.

- Global implementation strategy: carrying out a detailed process to develop a CBD implementation strategy, globally and regionally, to identify specific problems, needs and actions at both global and national level, along with a set of enabling environments covering national plans, actors and delivery mechanisms, within both existing programmes and new initiatives. Such a strategy should also include consideration of the legal elements of protected areas and a more deliberate assessment of the costs of implementation and the “gap” in financing so that the problem can be properly addressed.

- Regional focus and new partners: identifying partnerships to build programmes (including transboundary programmes), technical support, capacity development plans, field-based learning networks, exchange visits, best practice guidelines, donor roundtables etc modelled on initiatives in Micronesia, the South American 10 million hectare Challenge, Caribbean Challenge,, Altai-Sayan, Dinaric Arc, Caucasus, Carpathians, West Africa etc. Closer linkages with existing protected area initiatives such as those in Europe and Asia should be encouraged, possibly through WCPA regional groups.

- National consortiums to help implementation: (COP 9 Decision (IX/18) – 5.b) encouraging Parties to work with stakeholders to draw together national inter-sectoral advisory committees, including cross-ministerial links and government officials outside environment agencies, to plan an implementation strategy with objectives, membership and a realistic timetable linked to international targets. Other important stakeholders include local government, local community and indigenous peoples’ representatives, academics and NGOs. It should be noted that in many countries PoWPA is still only poorly recognised by many protected area managers.

- Cross-CBD linkages: (COP 9 Decision (IX/18) 5.b.v) increasing linkages with other CBD programmes perhaps through agreed targets and cross referenced work programmes, for example relating to agrobiodiversity, climate change, marine, mountains, forests, freshwater and fisheries; also the application of the Malawi Principles regarding the Ecosystem Approach and the Addis Ababa Guidelines and Principles. Such linkages should also relate ICCAs to agreements relating to Access and Benefit Sharing, Traditional Ecological Knowledge and REDD. The specificities of each biome make lesson-sharing between countries particularly important.

- Cross-convention linkages: repeating the success of current links with conventions (e.g. Ramsar) by closer cooperation with e.g. UNFCCC (possibly with an inter-convention action plan), UNCCD, CITES, World Heritage, Ramsar and MAB); for example by encouraging these conventions to reflect PoWPA in their own programmes, websites and publicity.

- Communications: (COP 9 Decision (IX/18) 5.b.iii) working out how values of protected areas can be better identified and communicated more effectively at regional and local level, using new media and networking opportunities, cooperation between different protected area agencies, the internet etc. Such work could include close cooperation between the CBD Secretariat, Friends of PoWPA, WCPA and also the IUCN Commission on Education and Communication.

- Building capacity: (COP 9 Decision (IX/18) 5.b.vi and 13) capacity building for PoWPA implementation needs to be increased, both in terms of effort and the precision with which it is focused on practitioners. Efforts should build on ongoing work at national and regional level: for example, existing training colleges, regional protected area expert networks and centres of expertise could be integrated more effectively in capacity building for PoWPA implementation. It should also reaffirm COP 9 decisions relating to the CBD web site, translations and production of training material to fill current gaps. This effort should include a particular element focusing on implementation of objective 2, covering participatory approaches, governance aspects, monitoring and reporting needs, resettlement issues etc.

- Strengthening regional networks and institutions: several regional initiatives exist, e.g. Carpathian Convention, Alpine Convention, Caucasus Biodiversity Council, Dinaric Arc Initiative, CCAD, SPREP, REDPARQUES, etc. Many of these organisations and networks have already been engaged in regional planning for PoWPA implementation, capacity building, exchange of lessons learned etc. In some cases they are linking to and supporting national-level consortia aimed at PoWPA implementation. Experience shows that such approaches are extremely effective in motivating governments to implement the PoWPA, building capacity and exchanging lessons learned.

- Global support mechanisms: the CBD Secretariat has been effective in engaging partners informally through PoWPA focal points and also the “Friends of PoWPA” to collaborate on implementation activities. There is also excellent collaboration between some global organisations on the ground at the national and regional level. This could be built on and strengthened by developing a more systematic approach to collaboration, which would set up a global coalition of key protected area stakeholders (including indigenous peoples and local community organisations) that would promote greater synergies and collaboration between key actors and support regional and national consortia. Moreover, the LifeWeb Initiative can serve as a useful strategy to strengthen implementation by encouraging and recognising new and additional funding for protected areas, facilitating funding matches between priority needs and committed donors; help coordinate donors’ support for large-scale projects; and promote the integration of protected areas as elements in national strategies to address climate change mitigation, adaptation and sustainable livelihoods.

( TARGET AND TIMETABLE ISSUES

It is proposed that Parties set their own national and where possible quantitative and time-bound targets (COP 9 Decision (IX/18) 5.b.ii), under a framework of regional and global targets. A number of global deadlines have been suggested, including a five-year extension on current targets, a staged series of deadlines over the next fifteen years and a general 2020 deadline. In addition, key targets from the PoWPA, and timelines to review implementation, should be included in the CBD’s larger post-2010 Strategic Plan. The various options need to be analysed and a set of recommendations developed.

( FUNDING OPPORTUNITIES

This should note the COP 9 Decision (section B) on identifying effective systems for financing capacity development and long-term management. It will require, for example, better application of financial gap analysis and business plans, investigation of costs and benefits and livelihood aspects, including especially with respect to climate change, and frequently also integration of protected area management into regional and local processes. The following funding opportunities require elaboration:

- LifeWeb: encouraging current donors to continue or increase their support and new donors to commit new and additional funding for protected areas, including priorities profiled on the LifeWeb clearing-house. Recipients should also be encouraged to profile their needs strategically, based on priorities identified through early actions in PoWPA implementation. The LifeWeb Initiative should be encouraged to provide the service of profiling needs; facilitating funding matches between recipients and committed donors; and promoting the integration of protected areas in national strategies to address climate change mitigation, adaptation and sustainable livelihoods.

- New funding opportunities: under UNFCCC, PES etc, providing clarification and then preparation of guidance to protected area agencies, indigenous peoples and local communities involved in protected area management and developers of national REDD and climate adaptation strategies about the range of possibilities under existing and new schemes. These might include in addition to possible climate-related funding for instance infrastructure offset taxes, ecological value added taxes, water funds, oil taxes, protected area fees etc.

- GEF funding: including the likely priorities of future GEF programmes and of major donors that supply co-funding to GEF. Since GEF funding is directed towards developing financial sustainability, follow up projects need to be planned properly and implemented effectively to achieve financial sustainability. As per an information document for GEF Council’s 35th meeting, countries have still not used all the allocation available under the biodiversity portfolio of GEF 4 Resource Allocation Framework; so the problem is not only adequate funding, but timely and appropriate use of available funding.

- GEF Early Action Grants: investigating options for development of a further Implementation Action Grant fund, to address identified implementation priorities based on results of Early Actions and corresponding assessments, which could be conveyed/profiled via the LifeWeb Initiative. The possibility that some of this money could be earmarked explicitly for innovative protection mechanisms, such as Indigenous and Community Conserved Areas, should also be investigated.

- Commitment from CBD Parties to protected areas: as with aid budgets we could consider suggesting a minimum percentage of GDP that countries devote to protected areas, at home and abroad.

- Leveraging development funds by linking protected areas to ecosystem services: investigating the opportunities to access new funding streams, including from private sources and Payment for Ecosystem Services mechanisms, to realise the economic potential of protected areas.

- Emphasise values and incentives: making efforts to understand and gain recognition for the economic values of protected areas, through links with initiatives such as The Economic of Ecosystems and Biodiversity (TEEB) study, PACT-2020 to help encourage governments; and analysis of the costs of ecosystem destruction e.g. from the Millennium Ecosystem Assessment.

- Climate finance: including protected areas as a key component of markets for emission permits, offsets and adaptation funds, and using ecological gap analysis to help identify priority investments from a climate perspective. This should emphasis “other” sequestration mechanisms, such as marine, peat, freshwater, grasslands and soil. Such financing needs to include mechanisms for ensuring that all concerned actors are comfortable with the choices and with national implementation strategies.

Appendix 1: PoWPA Implementation Challenges and Recommendations

| Issue | Discussion | Recommendations for future success |
| --- | --- | --- |
| Lack of commitment by governments, NGOs and PA Agencies to implement | Generally policy frameworks have been put in place in particular where guidance, methodologies and best practice exist (e.g. legal frameworks, gap analysis, management planning and management effectiveness) but implementation of policy and/or assessment findings is hard to judge. Issues to be addressed: lack of clear understanding of country commitments and obligations low national priority for protected areas and lack of understanding about protected area benefits, goods and services and their contribution to sustainable development unstable political situation lack of regional cooperation | Implementation strategies; ideally developed at a regional level to help foster regional cooperation and implementation National consortiums working with PoWPA focal points to implement and report progress and share best practice Communication of protected areas benefits; and encouragement of economic assessments (such as TNCs Valuing Nature campaigns) to help raise awareness |
| Lack of integration into regional/national PA priorities and plans | Problems relating to integration focus around: lack of inter-sectoral coordination conflicting national legislation and policy lack of multi-stakeholder coordination mechanisms lack of transparency in decision-making process | More regional support for governments through better established regional and national networks and “Friends of PoWPA” partnerships to highlight best practices, provide advice and aid implementation to support the development of better enabling environments for PAs |
| PoWPA not integrated with major PA projects/ programmes (including CBD processes) | Problems of concurrent programmes within CBD related and other conventions, PA projects and programmes with similar issues resulting: in confusion about who/how issues are addressed (e.g. MPAs are falling between two programmes; PoWPA and the Marine and Coastal Programme of Work); and different strategies for implementation being suggested/implemented. In other cases PA goals and opportunities are not adequately reflected in work programmes and funding mechanisms. | The revised PoWPA should consider and where possible be aligned to major funding initiatives (i.e. GEF-4, Life Web) and related UN processes (e.g. outcomes of Copenhagen COP 15; related discussions at CBD COP 10). |
| Deadlines difficult to achieve in countries with low capacity | There is an estimated 60% to 70% funding gap for effective implementation of the PoWPA. The perceived lack of funding is exacerbated by countries not developing strategies to secure long-term funding for their national PA systems. Although capacity remains an issue in relation to some of the very ambitious targets of the PoWPA; the main restraints in implementation associated more with lack of tools/guidance/best practice (i.e. in relation to theme 2). There is also clearly always going to disparity between rates of implementation between different countries which have well-developed and managed PA systems and those that do not. The PoWPA thus should consider reviewing not just achievement of targets but progress toward achievement. | There is a need for greater priority in developing needs assessment; funding strategies; financial and business planning. As this is a priority for GEF4 there is a major opportunity to work with Parties to develop appropriate financial planning and funding. Various other forms of capacity development are also required in relation to elements of the PoWPA which are not being adequately implemented – tools need to be urgently developed and field tested (i.e. in relation to costs and benefits) – see below. |
| Perception that PoWPA is complex (i.e. 92 activities) and difficult to implement | The PoWPA is currently presented as a long list of activities with the linkages between goals and actions not always obvious. It is thus perhaps not surprising that programme 1 has been more effectively implemented than programme 4. | The elements of the PoWPA need to be presented in a way that is more coherent as an overall plan for managing protected areas: individually, nationally, regionally and globally. |
| Lack of detailed action plans at national and regional levels for implementation | This issues related to the one above but also reflects the need for capacity development, additional tools and guidance, etc. |  |
| Many indigenous, traditional groups attacking PAs and PoWPA | Programme 2 of the PoWPA which relates to issues of governance, participation, equity and benefit sharing remains the most under implemented part of the programme; problems include: inadequate involvement of indigenous and local communities in PA planning and management local community resistance to protected areas governments not embracing the wide range of governance types in PA strategies | Various strategies could be developed, including: Statement of areas of mutual interest, agreed processes etc between some indigenous peoples organisations and PoWPA implementers Better reporting and dissemination of information in relation PAs designated/managed by indigenous and traditional peoples Better reporting on (and progress on) how countries strengthen and diversify their governance types (and highlight best practices from Colombia, Canada, Australia, Brazil etc) Better guidance and capacity building required in relation to the assessment and equitable sharing of costs and benefits (see point 10) |
| Lack of accurate reporting on PoWPA implementation | Various gaps in reporting (either relating to the reporting format or to lack of precise targets to report against in the PoWPA) have been highlighted by the CBD, including: Reporting to the CBD on management effectiveness (ME) – although a separate study on this has been undertaken by the University of Queensland and NGO partners On various targets within programme 2 | Where projects/processes are already in place to report on issues (such as the WDPA and ME module on the WDPA) reporting could be harmonised (e.g. ME Global study could become the official reporting tool for PoWPA implementation). Other initiatives, such as UNEP-WCMC transboundary protected areas inventory 2007 have proved a better source of data than country reporting. |
| Lack of clear thresholds / baselines for achieving actions and targets | Reporting has been clearer for those targets with clear targets and deadlines; at present many of these relate to planning or assessments not to implementation. | Targets could be added to elements with less progress, e.g. programme element 2, and more targets could be focussed on implementation. |
| Lack of knowledge regarding PoWPA, dissemination of tools, best practice and training hampering implementation | In some cases the best practices envisaged in the PoWPA are not backed up by suitable guidelines and tools to implement the activities; although progress has been made there remains a lack of simple, easily understandable methods and guidance and for these to be accessible in local languages and backed up with training modules and best practices examples. Particular gaps relate to: methods for valuation of protected areas costs and benefit analysis | Advice, best practice and tools in relation to the assessment and equitable sharing of costs and benefits Many countries indicated a lack of expertise and capacity in evaluating goods and services of protected areas More translation of existing tools (asked for specifically in relation to ME tools) |

Appendix 2: Review of PoWPA implementation

The review below has been prepared by the CBD Secretariat. It is based on information received in annex III of the 65 fourth national reports prepared by Parties to the CBD and on information gathered from Parties and organizations in the PoWPA regional workshops. It should be noted that the percentage used in this report is that out of the total Parties for which information is available, either from the reports received or information gathered. In describing general progress, “nearly all” indicates at least 90 per cent, “most” indicates at least 70 per cent, “many” indicates at least 40 per cent, “some” indicates at least 15 per cent and “few” indicates less than 15 per cent.

### Goal 1.1: To establish and strengthen national and regional systems of protected areas integrated into a global network as a contribution to globally agreed goals

Target 1.1: To establish and strengthen national and regional systems of protected areas integrated into a global network as a contribution to globally agreed goals (timeline 2010 for terrestrial and 2012 for marine) Summary of progress: Fair progress to date globally for terrestrial; very little progress for marine areas. There are significant improvements in the terrestrial protected area coverage reaching 12.2 per cent of the global terrestrial area; more than half of world’s terrestrial eco-regions, 12 of the14 terrestrial biomes and nine of the 15 WDPA’s regions have more than 10 per cent of their area under protection; out of the 114 countries for which information is available, 68 countries have kept aside more than 10 per cent of their territory under protection; about 50 countries have either completed or in the process of completing a comprehensive gap analysis and are taking actions to implement the results of gap analysis. Key issues considered for assessing global progress: Gap analysis; Creation of new protected areas; MPAs.

Nearly all reporting countries indicated progress towards target 1.1. By 2008 there are more than 120,000 nationally designated protected areas covering 21 million km2 of land and sea. While the terrestrial protected areas listed in WDPA cover 12.2 per cent of the planet’s surface area; the marine protected areas occupy only 5.9 per cent of the world’s territorial seas and only 0.5 per cent of the extraterritorial seas. Out of the 15 regions of the world recognized by the UNEP-WCMC, nine regions (Americas, East and Southeast Asia, Eastern and Southern Africa, Western and Central Africa, Europe, and the Caribbean) have 10 per cent of their terrestrial area under protected areas, whereas only three (Australia/New Zealand, South America and North America) of the 15 regions have more than 10 per cent their marine areas protected. Based on the information available from National Biodiversity Strategy and Action Plans and national reports, coverage of protected areas as a percentage of a country’s terrestrial area is available for 114 CBD Parties. 68 countries out of this total 114 have kept more than 10 per cent of their territories under protection (with 33 countries having more than 15 per cent of their terrestrial area protected); 23 per cent (26 countries) have 5 to 10 per cent and only 14.5 per cent of countries (six in number) have less than 5 per cent of their land designated as protected areas.

An overlay of nationally designated protected areas with the world’s terrestrial ecoregions reveals that 12 out of the 14 terrestrial biomes have more than 10 per cent of their area protected. Flooded grassland and Savannas biome with 42 per cent of its area under protected coverage is the highest protected biome.. Only tropical and sub-tropical coniferous forests biome and temperate grasslands, savannas and scrublands biome recorded less than 10 per cent protection with the latter has just about 5 per cent of its area under protection. However, the degree of protection to the ecoregions within these biomes vary, as out of the 825 terrestrial ecoregions more than 5 per cent are completely protected, 50 per cent have 10 per cent of their area protected and 8 per cent have less than 1 per cent of their area under protection . Out of the 232 marine ecoregions, only 39 per cent of them have 10 per cent of their area under protection, whereas 50 per cent have less than 1 per cent of their area under protection. Considering the current annual growth rate of marine protected areas (4.6 per cent) achieving the 10 per cent target of the CBD strategic plan and the PoWPA marine target may well be nigh impossible within the next 20 years.

More than 15 countries have completed a comprehensive ecological gap analysis and are in the process of implementing the results, whether by establishing new protected areas, extending existing protected areas, or by other means. In about 23 countries, attempts are underway to undertake comprehensive gap analyses. In some developed countries (Australia, Finland, Canada, and Germany) and in some developing countries (Brazil, Bhutan, Costa Rica) the protected area network is near comprehensive and ecologically representative covering major biomes (forests, pastures, deserts, grasslands, mountains, and wetlands) and includes public, private and community protected areas. Under-represented ecosystems typically include: coastal areas, oases, cave systems, karsts, grasslands, rivers and river canyons, marshes, and most significantly, marine systems. 27 countries reported the establishment of about 5,900 new protected areas – national parks, nature reserves, nature conservation areas, nature parks, landscape reserves, natural monuments, protected landscapes, ecological lands, scientific reserves and areas of community importance and 50 marine protected areas, covering approximately 60 million ha of terrestrial and marine areas, since 2004 ( Table 2 ). A majority of reporting countries have indicated plans to establish additional protected areas and to adopt targets for protected areas. These targets have been included in relevant environmental policies, national strategies for sustainable development, national biodiversity strategies, national wildlife action plans and programmes. The planned expansion of coverage ranges from 5.74 per cent to 30 per cent of the total geographical area of countries.

Table 2: Number and coverage (where available) of protected areas established since 2000/2004

| Country | PAs as % of land areas | Protected area (s) |
| --- | --- | --- |
| Brazil | 7% | 54 new federal PAs established and 9 existing Pas expanded covering 19.6 million ha. From 2000-05 State Pas increased 28.3 per cent in number and 64.7 per cent increase in size approximately 11.8 million ha. |
| India | 4.7% | 14 new PAs or an increase of 15 per cent in number covering 0.1 million ha. |
| Hungary | 9.4% | 93 new PAs (21 nature reserves, 71 protected natural areas of local significance, 1 landscape protection area) covering 26953 ha area. In addition 6 new Ramsar sites covering 79,000 ha area. |
| Mexico | 11.8% | 47 new national parks covering 7.2 million ha |
| Poland | 32.3% | 1029 new PAs ( Natural Reserves 116, documentation sites 50; ecological sites 572; natural landscape complexes 37; protected landscapes 5; Special Bird protection areas 69; special areas under habitat conservation 180 |
| Australia | 10.52% terrestrial 7% marine | National Reserve system has grown from 10.52 per cent in 2004 to 11.6 per cent in 2006; an increase of 9.11 million ha with 1280 new PAs. 43 new MPAs covering 24 million ha |
| Canada | 9.4% terrestrial 0.64% marine | About 15 million ha increase in area from 2005 to 2009 |
| China | 15% | 136 new PAs from the end of 2006 to the end of 2007 covering 34 million ha. |
| Spain | 8.8% | 184 new PAs covering 6.9 million ha (72 new SPAs for birds; 96 new protected natural areas; 16 new Ramsar sites). Area under Natura 2000 doubled from 5.5 to 11 million ha. |
| France | 12% | 1201 new PAs including Natura 2000 sites, National Parks, regional nature reserves, prefectural protection biotopes, forest biological reserves covering 6.84 million ha |
| Sweden | 10% | 21 new MPAs. 280000 ha of productive forests protected by the end of 2008. Proposals to establish 17 new national parks, extension of 7 existing parks and 28 new MPAS by 2010. |
| Philippines | 13.8% | 730 new MPAS from 1997-2007 with 48 per cent increase in the area. A 5.3 per cent increase in the proportion of terrestrial protected areas to total land area from 1992 to 2008. The proportion of forest cover to land area increased from 23.9 per cent in 2003 to 52.6 per cent in 2006. |
| Czech Republic | 18% | 43 new PAs (2 national nature monuments, 1 national nature reserves, 9 nature monuments, 14 natural reserves, 1 SPA and 16 SCI. |
| Germany | 13.5% terrestrial 41% marine | 749 new PAs ( 588 nature conservation areas, 2 national parks – Eifel and Kellerwald, 152 landscape reserves and 7 nature parks) covering 0.7 million ha |
| Finland | 15% | Since 2004 added 845,000 ha of new PAs in national parks, strict nature reserves, protected peat land areas and herb rich forest areas. |
| Rwanda | 10% | 2 new PAs (Ramsar site – Rugezi-Bulera-Ruhondo complex and Buhanga reserved forest area) |
| Norway | 14.3% | 234 new PAs covering 1.2 million ha. |
| Madagascar | 10% | 2 million ha of new PAs including 5 new MPAs |
| Albania | 9.8% | 6 new PAs since 2004 ( 2 managed nature reserves coastal wetlands, 1 protected ) ; expansion of Dajti national park and Mali me Gropa-Bize-Martanesh protected landscape |
| Algeria | 24% | 2 new Pas (one terrestrial national park and one marine nature reserve) |
| United Kingdom | 10.9% | 814 new PAs (19 special protection areas, 47 special areas of conservation, 2 Ramsar sites, 62 SSSIs +ASSIs, 6 national nature reserves, 668 local reserves, 9 areas of outstanding natural beauty and 1 national park) covering 0.8million ha. |
| Cameroon | 15% | 8 new Pas since 2001 |
| Estonia | 18% | 62 new Pas with an increase of 6 per cent in the coverage of Pas as percentage of territory. |
| Kyrgyzstan | 5.2% | 143,000 ha increase in PA coverage from 2005-2008 |
| Mongolia | 14.1% | An increase of 3 per cent in the coverage of PAs as percentage of territory. |
| Belgium | 12.6% | 77 new PAs ( 66 reserve areas, 6 Natura 2000sites and 5 wetlands) covering 48,470 ha |

### Goal 1.2: To integrate protected areas into broader land- and seascapes and sectors so as to maintain ecological structure and function

Target: By 2015, all protected areas and protected area systems are integrated into the wider land- and seascape, and relevant sectors, by applying the ecosystem approach and taking into account ecological connectivity / and the concept, where appropriate, of ecological networks.

Summary of progress: Some progress to date may likely to be achieved by the date provided more systematic effort are put in place in next five years.

Key issues considered for assessing global progress: measures taken for developing enabling environment for integrating protected areas into broader land and seascapes and sectors; application of ecosystem approach.

Progress towards achieving this target is more evident in Europe and a few other developed countries. The majority of reporting countries indicated enabling legislative, policy measures and tools for integrating protected areas into broader land and seascapes and sectoral interests. Some examples include: the Protected Areas Act in Albania; the Directions for the National Reserve System-A Partnership Approach in Australia; Directives under beyond sites requirement of the European Commission Bird and Habitat Directives -Natura 2000 in European Community member States; Article 3 of the Federal Nature Conservation Act in Germany; the National Natural Heritage Plan in France; Strategic Environmental Assessment in Lebanon; and the Ecological Network Act in Ukraine.

In many countries, protected areas are integrated into surrounding areas through regional development planning, spatial planning, including establishment of ecological corridors, core areas, buffer zones and Biosphere Reserves. Many reporting countries indicated they had taken steps to improve connectivity and ecological networks. Some examples include: Australian Alps to Atherton (A2A connectivity conservation corridor); Greater Mekong sub region Biodiversity conservation corridor in Viet Nam; ecological green corridors in Hungary; eco-tunnels and eco-passages in Belgium. Many developing countries reported that on a conceptual level, the need for adopting the ecosystem approach and establishing/managing protected areas in the regional context is well understood; however, in practice the sectoral interests and competing land uses make it difficult to integrate protected areas into broader land and seascapes. Information on integrating marine and coastal protected areas into surrounding seascapes has not been well reported.

### Goal 1.3: To establish and strengthen regional networks, transboundary protected areas (TBPAs) and collaboration between neighbouring protected areas across national boundaries

### Target: Establish and strengthen by 2010/2012 transboundary protected areas, other forms of collaboration between neighbouring protected areas across national boundaries and regional networks, to enhance the conservation and sustainable use of biological diversity, implementing the ecosystem approach, and improving international cooperation.

### Summary of progress: Fair to good progress to date globally, 34 per cent increase in number of transboundary protected areas complexes, partially achieved at global level.

### Key issues considered for assessing global progress: Increase in the number of transboundary protected areas established; the kinds of collaboration across national boundaries.

The UNEP-WCMC transboundary protected areas inventory (2007), based on reviewing the digital maps of WDPA, identified 227 Transboundary Protected Areas Complexes (TBPA) incorporating 3,043 individual protected areas. Based on GIS analysis the total area TBPA was estimated as 4,626,601.85 km2 with 63 per cent of this occurring in both continents of America. Africa and Asia recorded about 32 per cent and the Europe has only 5 per cent of this total area. The TBPA complex “Ellesmere/Greenland between Canada and Greenland is the biggest TBPA complex in size covering 1,008,470.127 km2. With 169 TBPA in 2001 their number increased to 188 in 2005 and to 227 in 2007 a 34 per cent increase in number since 2001.

Zbicz (2005) identified six “hierarchical, increasing levels of transboundary cooperation between adjoining protected areas”: (i) no cooperation, (2) communication, (3) consultation, (4) collaboration, (5) coordination of planning, and (6) full cooperation. A global survey of managers working in TBPA according to this system found that at the extremes, 18 per cent responded that there was no cooperation at all, while 7 per cent were cooperating at the level of “full cooperation.” 39 per cent of respondents indicated that they at the level of “communication.” Zbicz drew out four “factors” correlated to the level of cooperation. In essence, higher levels of cooperation occurred (1) if the idea of transfrontier cooperation and ecosystem-based management was important to the protected area managers and personnel, (2) if there were adequate communication technologies in place, (3) if there were individuals willing to take leadership roles, and (4) if land managers were able to make personal contact across the border. Not surprisingly, it was the latter factor that correlated most strongly with the level of cooperation achieved.

Nearly all reporting countries indicated collaboration with neighbouring countries in establishing transboundary protected areas and regional networks, as well as cross-boundary management agreements. Multilateral environmental agreements such as the Convention on Migratory Species, the Convention on International Trade on Endangered Species, the Ramsar Convention on Wetlands, along with the Convention on Biological Diversity, as well as many other regional instruments, including the Protocol Concerning Specially Protected Areas and Wildlife, the Barcelona Convention, and the Alpine Convention provided suitable frameworks for regional cooperation that facilitated the achievement of this target.

Important regional protected area networks include the Meso-America Regional Network, the Alpine Protected Area network, the Pan European Ecological Network, the Central Africa Network of Protected areas, the Marine Protected Areas Network for the Western Indian Ocean Countries, and Transnational River Basin Districts on the Eastern Side of the Baltic Sea Network. Transboundary initiatives include inter alia: ZIMOZA (Zimbabwe, Mozambique and Zambia) Trans-boundary initiative; KAZA (Namibia, Botswana, Zimbabwe, and Zambia) initiative; the Gobi desert reserves and Altai mountain reserves between China and Mongolia; trans-frontier marine conservation between Tanzania and Mozambique; Danube Delta and Prut river initiative between Romania, Ukraine and Moldova; Eastern Carpathian migratory corridor (Polish-Slovak-Ukrainian Biosphere Reserve); transboundary protected areas between Eritrea, Djibouti and Somalia; the intercontinental Biosphere Reserve of the Mediterranean Andalusia (Spain) established in 2006 and The East Asian-Australasian Flyway.

### Goal 1.4: To substantially improve site-based protected area planning and management

Target: All protected areas to have effective management in existence by 2012, using participatory and science-based site planning processes that incorporate clear biodiversity objectives, targets, management strategies and monitoring programmes, drawing upon existing methodologies and a long-term management plan with active stakeholder involvement.

Summary of progress: Fair progress to date with about 30 per cent of national protected areas has management plans in place and another 30 per cent are under development, but effective implementation of plans are lagging behind. Likely to achieved partially by the target date of 2012.

Key issues considered for assessing global progress: Percentage of protected areas (area and number) have science based management plans; their preparation through stakeholder involvement; and implementation

In general, reports indicated that science-based management plans exist for at least 30 per cent of protected areas and management plans are under development for an additional 30 per cent. Some examples are given below. In some reporting countries, development of management plans is a statutory requirement and almost all of their protected areas either already have management plans or plans are under development. However, in nearly all developing countries, and in some developed countries, lack of sufficient human and financial resources is a major impediment to the effective implementation of management plans. Most of the reporting countries developed guidelines and approaches for developing management plans and used participatory approaches that included the input of various stakeholders while developing the plans.

Table 3: Development of management plans

| Country/Region | Number of protect areas having management plans (MPs) |
| --- | --- |
| Australia | All jurisdictions seek to develop PA management plans. South Australia State recorded an increase from 42.8 per cent to 61.7 per cent in the last ten years and planning to achieve state wide coverage by 2011. Victoria State approved MPs for 13 MPAS and 11 marine sanctuaries by 2007. |
| Albania | 3 national parks have MPs |
| Bhutan | 6 out of the 9 national parks have MPs |
| China | Many protected areas developed MPs but many of them have not been implemented due to various impediments. |
| Colombia | 50 out of 51 protected areas have MPs and they are being implemented |
| EC | 5312 of Natura 2000 sites have MPs, for another 3250 sites MPs are under development |
| Estonia | For 25 protected areas MPs are under effective implementation, for 35 protected areas MPs are under development. |
| India | For national parks 39 per cent have MPs; 22 per cent are under preparation. 39 per cent have no management plans. For wildlife sanctuaries 34 per cent have plans; 16 per cent under preparation and 50 per cent no plans. Annual plan of operations are prepared for all protected areas. |
| Spain | 40 per cent of protected areas have MPs |
| Sweden | 75 per cent of Natura 2000 sites have conservation plans |

### Goal 1.5: To prevent and mitigate the negative impacts of key threats to protected areas

Target: By 2008, effective mechanisms for identifying and preventing, and/or mitigating the negative impacts of key threats to protected areas are in place.

Summary of progress: Fair to good progress to date in identifying the threats, but threat mitigation and prevention are lagging behind globally.

Key issues considered for assessing global progress: Status of threat assessment; actions to improve threat prevention and mitigation.

Nearly all reporting countries have established at least some measures to identify prevent and/or mitigate the negative impacts of threats to protected areas, however, the level of detail varied considerably. In general, threats to protected areas are identified through threat reduction analysis as part of the management plan for individual protected areas. Threats are also identified through routine field patrols by staff, community members or members of the public. Threats to protected areas and their levels vary from country to country. Prevalent threats include habitat fragmentation, conflicting adjoining land use, invasive alien species, mining and oil drilling, pollution, altered fire and hydrological regimes, legal and illegal logging, visitor impacts, hunting, and farming practices. Many countries in the 4th national reports highlighted climate change as one of the most significant threats.

Regarding prevention and mitigation measures, many countries reported that they have developed legislative, policy and regulatory measures, including mandatory environmental impact and strategic environmental assessment of development projects and incentive schemes. Some countries indicated that prevention and mitigation of threats is accomplished through pre-emptive actions in the threat-reduction analyses, including sharing of responsibility between protected-area staff and local communities, and conflict resolution. Many countries reported that they were undertaking measures to restore and rehabilitate the ecological integrity of protected areas. Some examples include: boundary demarcation; selective salvage operations in forest reserves; replanting with indigenous species; strict law enforcement; conversion of water balance in bogs and fens; establishment of grazing systems in grasslands; removal of shrubs and trees from high value grasslands, bogs and fens; and coral-reef mooring.

### Goal 2.1: To promote equity and benefit-sharing and Goal 2.2: To enhance and secure involvement of indigenous and local communities and relevant stakeholders

Target 2.1: Establish mechanisms for the equitable sharing of both costs and benefits arising from the establishment and management of protected areas (by 2008)

Target 2.2: Full and effective participation of indigenous and local communities, in full respect of their rights and recognition of their responsibilities, consistent with national law and applicable international obligations, and the participation of relevant stakeholders, in the management of existing, and the establishment and management of new protected areas (by 2008)

Summary of progress to date: Some progress to date in both the targets but way behind meeting the targets at global level and also at regional level except pacific islands region.

Key issues considered for assessing the progress: assessment of socio cultural costs and benefits of protected for indigenous and local communities; recognition of governance types and community conserved areas; mechanisms for full and effective participation of indigenous and local communities.

Although one can conclude that these two targets of the Programme Element 2 are not achieved at the global level, but the principles of equity, participation, governance and sharing of costs and benefits are increasingly being considered at national levels and being incorporated into national policies.

Nearly all countries reported having legislative and policy frameworks for the equitable sharing of costs and benefits arising from the establishment and management of protected areas. However, few countries provided details and many countries indicated gaps in terms of equitable sharing of costs and benefits. One country (Australia) indicated that all its states and territories have enabling legislation related to conservation covenants on the title of private lands. Some countries established joint/collaborative/ participatory forest management programmes, tourism ventures etc, to share revenues with local communities. Assessments of economic and socio- cultural costs and benefits of protected areas for indigenous and local communities have not been undertaken in the majority of reporting countries. Some countries reported undertaking measures to avoid and mitigate negative impacts on indigenous and local communities through the establishment of protected areas, which inter alia include alternate livelihood options; acquisition compensation grants; covenanting programmes and revolving funds; and development of regulations to protect the rights and interests of indigenous and local communities.

A majority of responding countries reported that their relevant laws and policies incorporate a clear requirement for the participation of stakeholders and indigenous and local communities in the planning, establishment and management of protected areas. A few countries also reported that a process of public consultation particularly with local communities is undertaken at national or local level before protected areas are established. In general, multi-stakeholder protected areas advisory committees or conservation boards are important mechanisms to facilitate participation of all stakeholders. Many countries indicated measures taken to support indigenous and community conserved areas (ICCAs), which inter alia include training, assistance through non-governmental organizations, dissemination of information, and funding. However, not much information is available regarding how many countries accorded recognition to ICCAs and co managed protected areas. A survey of 16 countries by IUCN-WCPA TILCEPA found six countries (Australia, Brazil, Guyana, India, South Africa and Vanuatu) enacted legislation recognizing ICCAs as part of the country protected area network. Another six countries (Canada, Costa Rica, Indonesia, Mauritania, Tanzania and Taiwan) provided legal backing to ICCAs, but as part of more general laws providing recognition of indigenous or community territories, rather than as protected areas or specific conservation mechanisms. Four countries (China, Morocco, Nepal and Nigeria) had no legal backing for ICCAs, but provided some level of administrative support. While there is some progress in terrestrial ICCAs, community managed marine protected areas, except the Locally Managed Marine Areas (LMMAs) in the Pacific, are not well developed in other regions.

Information on how countries strengthened and diversified their governance types is not available barring few. For example, Colombia has moved towards much greater participation of indigenous peoples, peasant communities, and others. It also encouraged the creation and incorporation of a complex set of regional and local reserves, collaboratively managed PAs, indigenous territories, private protected areas, and community conserved areas. Australia has established 22 indigenous protected areas covering 14 million hectares and implementing new forms of conservation and covenanting programmes. Canada has established First Nations protected areas. Madagascar has also moved into diversifying PA governance types and India extended its PA types to include those that could be managed in a collaborative manner with various government departments and local communities, and those to be managed by local communities themselves. India has established 43 conservation reserves and community reserves. Brazil has reported that there are 65 indigenous lands in the community conserved areas of which 38 are demarcated and 28 are legally established. Under UNDP/GEF PoWPA project currently 19 countries (Afghanistan, Antigua Barbuda, Armenia, Benin, Burundi, Cambodia, Comoros, DR Congo, Guatemala, Guinea, Honduras, Kiribati, Maldives, Mali, Mauritania, Micronesia Federated states, Samoa, Gambia and Uganda) are assessing and diversifying protected area governance types.

Diversifying the governance of protected areas, into collaborative and community based regimes, will be a significant step towards achieving the objectives of PoWPA but such diversification itself requires considerable effort on part of governments, international agencies, indigenous peoples and local communities, other civil society organizations, donors, scientific groups, and others. Grater documentation of best practices, facilitation of learning across countries and regions, utilizing and building on existing guidance, commitment to translate the policy into concrete actions, will ensure effective implementation of Programme element 2.

### Goal 3.1: To provide an enabling policy, institutional and socio-economic environment for protected areas

Target: By 2008 review and revise policies as appropriate, including use of social and economic valuation and incentives, to provide a supportive enabling environment for more effective establishment and management of protected areas and protected areas systems.

Summary of progress: Fair to good progress to date, partially achieved the target at global level

Key issues considered for assessing the progress: assessment of policy, institutional environment; kind of social and economic valuation methods and incentives to support enabling environment.

The majority of reporting countries indicated that they had already put in place appropriate policy, institutional and socio-economic frameworks for effective establishment and management of protected areas. Some countries have already enacted specific legislation for protected areas and some countries have done so specifically for marine areas. Though some countries indicated that they carry out valuation of goods and services of protected areas, and use various types of socio-economic valuation methods, information on how those values have been captured into national accounts has not been provided.

A number of tools are now available to assess the values and benefits of protected areas .

Some countries developed and tested social and economic valuation methods concerning the effects of protected areas for regional development. Many countries indicated a lack of expertise and capacity in evaluating goods and services of protected areas and their reflection in national accounts, e.g., gross domestic product and national budgets.

From the information provided, some of the main impediments for effective establishment and management of protected areas include lack of financial resources; lack of trained manpower and capacities; competing needs on land; lack of intersectoral coordination, lack of clear-cut roles and responsibilities; jurisdictional conflicts; compensation issues and land tenure rights and ownership regimes; high rates of human population growth and resource consumption; lack of political support; lack of public awareness and support; boundary disputes between traditional leaders; wildlife damage and strained relations between local communities and management authorities.

### Goal 3.2: To build capacity for the planning, establishment and management of protected areas

Target: By 2010, comprehensive capacity building programmes and initiatives are implemented to develop knowledge and skills at individual, community and institutional levels, and raise professional standards.

Summary of progress to date: Fair to good progress to date, could be partially achieved at global level.

Key issues considered for assessing the progress: comprehensive capacity needs assessments; programmes implemented for capacity building.

Nearly all countries reported advancement toward achieving this target. Nearly all countries reported undertaking capacity needs assessments and establishing capacity building programmes. In the majority of countries capacity building is an integral part of protected area management plans. In some countries, premier specialized training institutions have been established for conducting regular and customized training programmes for managers and frontline staff. Some of these institutions have been recognized as regional training institutions for the countries of the region. In some countries, training programmes are also developed for non-governmental organizations and community groups as well as government protected-area staff. In many reporting countries, project-based training programmes are implemented. A few countries indicated that they are undertaking multidisciplinary approaches in the management of protected areas by incorporating information from natural sciences, social, economic and political sciences, and traditional knowledge.

### Goal 3.3: To develop, apply and transfer appropriate technologies for protected areas

Target: By 2010 the development, validation, and transfer of appropriate technologies and innovative approaches for the effective management of protected areas is substantially improved, taking into account decisions of the Conference of the Parties on technology transfer and cooperation.

Summary of progress: Fair progress to date, could be partially achieved at global level.

Key issues considered for assessing the progress: development and transfer of technologies for protected areas.

Most countries reported the application of innovative approaches and technologies in the establishment and management of protected areas. In general these technologies include, remote sensing and Geographic Information Systems, habitat and landscape mapping, satellite telemetry, and camera traps. Some new approaches include public-private partnerships, management effectiveness-tracking tools, rapid assessment and prioritization of protected areas management, and the IUCN Management Effectiveness Framework. Some countries reported development of new concepts and technologies such as “field biotope network planning”, “ecological security”, and “landscape security”. Some countries reported development of integrated information management systems for protected areas for dissemination of information and approaches for effective management of protected areas. Many reporting countries indicated collaboration and sharing of information and technologies within the country and/or with other countries. Many developing countries called for regional collaboration, capacity and know how, and financial support for using innovative and new technologies

Goal 3.4: To ensure financial sustainability of protected areas and national and regional systems of protected areas

Target: By 2008, sufficient financial, technical and other resources to meet the costs to effectively implement and manage national and regional systems of protected areas are secured, including both from national and international sources, particularly to support the needs of developing countries and countries with economies in transition and small island developing States.

Summary of progress: Some progress to date but way behind meeting the target at global level and also at regional level.

Key issues considered for assessing the progress: financial needs estimates and status of development and implementation of sustainable finance plans; funding from bilateral and multi lateral sources.

Financial needs assessment and status of sustainable finance plans: The PoWPA requires Parties to develop and implement country-level sustainable plans for ensuring financial sustainability of national systems of protected areas. Assessment of financial needs and gaps is one of the first steps in developing sustainable finance plans. With a few exceptions, most of the reporting countries have not undertaken these assessments. Information on financial needs assessment is available for only 19 least developed countries, Small Island developing States, other developing countries and countries in economies in transition. Estimated annual funding gap for implementing PoWPA by these 19 countries ranged from US$ 3.28 million to 142.25 million. For developed countries information is available only for Australia and EC. The majority of responding countries indicated that a major source of funding for protected areas is national and provincial budgets. With only few exceptions, most countries, including developed countries, find resources limited or very limited for the establishment and management of protected areas. None of the reporting countries elaborated on the strategies that are in place or under development to secure long-term funding for their national protected area system. Very few countries indicated the nature of supplementary funding mechanisms. To date only few countries are in the process of completing country–level sustainable financing plans.

Under UNDP/GEF PoWPA project eight countries (Antigua and Barbuda, Belize, Djibouti, Dominican Republic, Honduras, Lao PDR, Micronesia, Mongolia, are currently developing sustainable finance plans.

Funding from bilateral, multilateral and other sources: Based on the available information, international financing for biodiversity conservation in recent years is estimated to be around US $ 4 to 5 billion annually with some 30 per cent to 50 per cent of it going to protected areas. Out of this, as much as 2 billion dollars - comes from high income countries’ Overseas Development Assistance (ODA) in the form of country-to-country bilateral aid, and in the form of multilateral aid managed by the GEF, other UN agencies, the International Development Agency and multilateral development banks. Not-for-profit funding, coming from international conservation NGOs, private foundations and businesses-related foundations, may contribute over 1 billion dollars annually but precise figures are difficult to estimate. Market-based sources include (a) international ecotourism and tourism, (b) markets for environment–friendly products (organic, certified, fair trade, etc) and (c) the incipient field of international payments for ecosystem services (IPES), like bio-prospecting and bio-carbon, may contribute to US$1 to 2 billion.

The Global Environment Facility is the largest funding mechanism for protected areas worldwide. GEF has invested in over 1,600 protected areas, covering more than 360 million hectares. The GEF has provided more than $1.56 billion to fund protected areas, leveraging an additional $4.15 billion in co-financing from project partners. In addition, the resources allocated to supporting PA system projects have increased during each successive GEF replenishment cycle In GEF -4 (2007-2010) approximately 450 million is allocated for protected area system. In addition other GEF initiatives such as the Small Grants Programme and the Critical Ecosystem Partnership Fund have also contributed significantly to protected areas. As per the guidance given by the COP in decision VII/28 the GEF launched a UNDP/GEF project to support implementation of PoWPA.

While there is increase in allocation under each GEF cycle, the share of biodiversity conservation under bilateral aid has remained fairly constant, between 2.4 per cent and 2.8 per cent of total bilateral ODA through the last 15 years. During the last meeting of the COP, the Government of Germany launched the LifeWeb, as a means to support and strengthen implementation of the PoWPA through new and additional financial resources. The government of Germany has committed approximately 120 million Euros over three years to support projects brokered through this initiative, within the framework of the International Climate Initiative. . The government of Spain has also recently committed 5 million Euros. A number of other donors have expressed interest in supporting projects brokered by the LifeWeb Initiative. The vision is LifeWeb will over time combine a diversity of donors, including public bilateral and multilateral agencies, foundations, and the private sector and become a ‘one stop shop’ for information and opportunity on protected areas financing. A small LifeWeb Coordination Office has been recently established within the CBD Secretariat in order to develop and manage the initiative.

### Goal 3.5: To strengthen communication, education and public awareness

Target: By 2008 public awareness, understanding and appreciation of the importance and benefits of protected areas is significantly increased.

Summary of progress: Fair to good progress to date partially achieved at global level.

Key issues considered for assessing the progress: Awareness raising activities; communicating benefits

Most countries reported undertaking at least some communication, education and awareness-raising activities for enhancing public understanding and appreciation of protected areas. In many countries conservation foundations and NGOs are supplementing governmental efforts in public awareness activities. In some countries both federal and provincial governments are engaged in education strategies and programmes in communicating the biodiversity and other values of protected areas. Public awareness activities included publication of brochures, booklets, posters, websites, CD-ROMs; organization of guided tours; engagement of folk art and cultural shows; construction and maintenance of nature trails, camping, mountain biking, recreational vehicle driving; competitions; observance of important days and festivals; establishment of conservation education/interpretation centres in protected areas, visitor centres, and “discovery ranger programmes” aimed at families gaining a first-hand experience of reserve values. One country reported development of a communication strategy for its national protected area system, including its marine protected areas. In many reporting countries, environmental education is introduced in the school curriculum. Information specifically on the inclusion of protected areas in the formal school curricula has not been provided.

### Goal 4.1 - To develop and adopt minimum standards and best practices for national and regional protected area systems

Target: By 2008, standards, criteria, and best practices for planning, selecting, establishing, managing and governance of national and regional systems of protected areas are developed and adopted.

Summary of progress: Fair to good progress to date in developing standards, criteria and best practices but lagging behind in adopting them at global level and also at regional level.

Key issues considered for assessing the progress: development of standards and criteria for planning, selecting establishing and managing protected areas and adopting best practices.

A few countries (15 per cent) reported having comprehensive standards, criteria and best practices for site selection, management and governance of protected areas. In some countries, monitoring protocols for some categories of protected areas have been formalized. With regard to the Natura 2000 network, a number of guidelines for site management have been developed at the level of the European Union. One reporting country indicated the approach undertaken in the systematic protection of marine areas and standards and best practices for new activities in terrestrial reserves. IUCN-WCPA has produced an extensive series of “best practice” guides for protected area establishment and has proposed a set of minimum standards for protected area management. As of now 16 best practice guidelines covering inter alia sacred natural sites to indigenous and community conserved areas, transboundary protected areas, mountain protected areas, management effectiveness, sustainable financing etc.

### Goal 4.2: To evaluate and improve the effectiveness of protected areas management

Target: By 2010, frameworks for monitoring, evaluating and reporting protected areas management effectiveness at sites, national and regional systems, and transboundary protected area levels adopted and implemented by Parties

Summary of progress: Some progress to date, but unlikely achieving the target at global and regional level by 2010.

Key issues considered for assessing the progress: Status of management effectiveness assessment; measures taken to implement results of assessment to improve management effectiveness.

Significant inter- and intra-regional differences among countries can be discerned in tracking the progress in this target. Within a region, some countries indicated significant advancement in carrying out management effectiveness evaluations. However in a number of countries within the same region management effectiveness assessment has yet to be undertaken. Most of the reporting countries indicated adoption of the IUCN-WCPA management effectiveness framework, and have adopted either the WWF Rapid Assessment and Prioritization of Protected Area Management (RAPPAM) methodology, or a scorecard approach, for carrying out assessments. Some countries strongly articulated the need for availability of these methodologies and tools in local languages and increased technical capacity for undertaking management effectiveness evaluations. Information on the percentage of the overall surface of protected areas that have been evaluated, or conclusions of evaluations and incorporation of the results of evaluations into management plans of protected areas, is not made available in the reports. However a global study undertaken by the University of Queens land, with support from WWF, TNC, IUCN-WCPA, UNEP-WCMC, has documented over 7,600 management effectiveness assessments from 128 countries. Detailed information on the outcome of the Global Study based upon the 2008 report and updated information provided by the University of Queensland and UNEP-WCMC for the GBO 3 is given below.

Global Study on Management Effectiveness Evaluation of Protected Areas

By obtaining original data, analyzing about 50 per cent of the total assessments and reviewing 50 evaluation reports, the Global Study developed a database, which is being linked to the WDPA. Majority of assessments are from Latin America and the Caribbean region ( over 2500), followed by Oceania, largely due to extensive ‘State of Parks’ studies in Australia (in NSW, Queensland and Victoria), Asia, Europe and Africa. To date few studies have been included from North America. Activity 4.2.2 requires Parties to implement management effectiveness evaluations at least 30 per cent of their national PA systems. Given this requirement, and the total number of assessments used in the Global Study comprise just under 8 per cent of the over 100,000 PAs included in the WDPA, achievement of the 30 per cent requirement of PoWPA by 2010 will fall short and the gap is substantial. However the Global Study found that assessments available for over 7600 PAs represent significant progress over the position of just a few years previously and there is evidence of many more countries commencing programs of evaluation.

Protected areas have been assessed using many different methodologies. In order to gain an overall picture, the Global Study developed a ‘common reporting format’, defining 45 headline indicators which represent the major themes and elements of the thousands of indicators used in the various assessment systems. There were clear patterns in the strengths and weaknesses of management amongst the 45 common reporting format indicators, and these patterns were consistent across most methodologies and regions. Highest scoring indicators overall were park gazettal, marking of boundaries, resolution of tenure issues, effectiveness of governance and leadership and the skill level of staff and other management partners. Weakest areas related to programs of community benefit, funding reliability and adequacy, management effectiveness evaluation, maintenance, communication, and community involvement. Many protected areas lack basic requirements to operate effectively, and do not have an effective management presence. Outcome indicators, relating to achievement of objectives, values conservation and effect on the community, also scored relatively well, indicating that even where ‘inputs’ and many ‘processes’ are weak, protected areas were still performing a valuable function for conservation and in the community. The most commonly nominated threats in most regions were hunting, killing and collecting animals; logging and wood harvesting; gathering non-timber forest products; recreational activities; and the management of adjacent lands. These show some consistency across regions, though differences are seen in countries like Australia, where invasive species and fire management are more serious threats. UNEP –WCMC in partnership with the Global Study created a webpage within WDPA to enable viewing of the methodologies and study locations (www.wdpa/org/ME/Default.aspx ).

### Goal 4.3: To assess and monitor protected area status and trends

Target: By 2010, national and regional systems are established to enable effective monitoring of protected-area coverage, status and trends at national, regional and global scales, and to assist in evaluating progress in meeting global biodiversity targets.

Summary of progress: Fair to good progress to date, in monitoring coverage and trends at national, regional and global scales through the World Database on Protected Areas (WDPA), but monitoring status is lagging behind.

Key issues considered for assessing the progress: mechanisms for monitoring and reporting; inputs to WDPA

A few countries (15 per cent) reported having mechanisms in place for monitoring the coverage, status and trends at national level. All reporting countries indicated that Environment Ministries are responsible for annually collating national protected area statistics and submitting information to WDPA, to other site based conventions and treaties such as Ramsar, World Heritage, Man and Biosphere Programme of UNESCO, CMS and CITES.. Some countries also indicated that monitoring programmes for rare and endangered species, trade in endangered species through TRAFFIC etc are put in place. At the EU level, a regional system of monitoring the coverage, status and trends of Natura 2000 network based on the data provided by the Member States when submitting the lists of potential sites and later in the periodic national reports.

### Goal 4.4: To ensure that scientific knowledge contributes to the establishment and effectiveness of protected areas and protected area Systems

Target: Scientific knowledge relevant to protected areas is further developed as a contribution to their establishment, effectiveness, and management.

Summary of progress: Fair to good progress to date.

Key issues considered for assessing the progress: Use of scientific knowledge and identification of research priorities for protected areas

Many reporting countries indicated extensive and appropriate use of scientific knowledge in establishment and management of protected areas including dissemination of information and knowledge to protected area mangers and field staff. The IUCN-WCPA, other major conservation organizations are constantly incorporating the scientific developments in conservation biology, ecosystem science and remote sensing applications in the best practice guidelines, tools and resources. Some countries have established specialised institutions for carrying out research in protected area related aspects. Some reporting countries indicated establishment of scientific advisory bodies and development of frameworks with scientific institutions. In some countries specialized courses at under graduate and graduate levels have been established in universities.

Appendix 3: Summary of COP 9 Decision IX/18

Concerning implementation of the PoWPA the COP 9 Decision (IX/18) asks Parties to:

4.a) Better integrate protected areas into broader land and seascapes and relevant sectors and plans, including aiming at poverty eradication (see also 19)

4.b) Give special attention to improving the management effectiveness of protected areas

- through capacity building measures,

- monitoring and evaluation of biodiversity at site- and system-level

4.c) Give special attention to the implementation of programme element 2

5.a) Transmit to the Executive Secretary information on sites they wish to designate as protected areas, with a view to mobilize enhanced financial support

5.b) Establish multisectoral advisory committees to support of the implementation the PoWPA and

  - Better coordinate and communicate among those involved with protected areas

  - Develop national targets and action plans for implementing PoWPA

  - Increase public awareness and develop a communication strategy for PoWPA (see also 22)

  - Monitor and report on implementation

  - Support coordinated implementation of PoWPA with other CBD programmes and biodiversity-related conventions

  - Support capacity building and fund programmes to improve PoWPA implementation

  - Identify policy and legislative barriers and knowledge gaps and improve conditions for implementation, i.e. innovative financial mechanisms, guidance, tools and strategies

6.a); b) and d) Improve, diversify and strengthen protected area governance types; recognize the contribution of co-managed protected areas, private protected areas and indigenous and local community conserved areas within the national protected area system and Establish processes for the full and effective participation of indigenous and local communities in the governance of protected areas

6.c) Promote the development and importance of ecological networks

6.e) Develop and implement measures for the equitable sharing of costs and benefits arising from the establishment and management of protected areas

6.f) Support the establishment or strengthening of regional or subregional forums that contribute to the effective implementation of the PoWPA

7) Facilitate and improve transfer of technologies to developing countries to enhance management effectiveness of protected areas

8); 9); 10) and 11) encourage UNEP-WCMC (the WDPA Consortium and IUCN) to main and improve the WDPA and help streamline national reporting on biodiversity; and ask Parties to develop national or regional data networks to facilitate the exchange of information and specifically to report on the refined IUCN categories

12) Calls for all involved to develop technical support networks for PoWPA implementation by:

- Making tools available

- Facilitating the sharing of public information and knowledge

- Supporting and/or coordinating subregional workshops

- Convening regional/subregional technical training on key themes of the PoWPA

- Enhancing partnerships and exchange programmes between agencies and protected areas

- Strengthening national and regional training institutions

13) Asks WCPA and others to strengthening national and regional capacity in training institutions to aid PoWPA implementation through the development of an open curriculum framework

14) Encourages Parties to consider the use of the UNEP/IUCN TEMATEA Issue-Based Module on Protected Areas in national implementation of agreements with regard to protected areas;

15) Requests the Executive Secretary to hold regional and subregional capacity-building and progress-review workshops on key themes and asks for financial and technical support for this

16); 17); 18) and 20) Requests the Executive Secretary, subject to the availability of funding, to further develop tools for PoWPA implementation aimed at different audiences and translated into all UN languages; and develop a user-friendly, comprehensive central website on PoWPA (including information related to 5a above and information on best practice on PoWPA implementation)

21) Requests Parties to designate a national focal point for the PoWPA to facilitate development and implementation of work on protected areas

23) Encourages Parties and relevant organisations to enhance research and awareness of the role of protected areas, and networks of protected areas, in addressing climate change

Concerning financial resources for implementation the COP 9 Decision (IX/18) notes that insufficient financial resources continues to be one of the main obstacles to the implementation of the PoWPA by developing countries and economies in transition; thus

- Parties are invited to: 3.a), b) and c) As a priority undertake country-level financial needs assessments, and develop and implement effective sustainable financing plans for protected areas; 3.d) Promote the valuation of ecosystem goods and services provided by protected areas, especially the socio-economic costs and benefits to indigenous, local communities and other stakeholders ; 3.e) Integrate and mainstream protected area planning and management within development agendas ; 3.f) Consider national fundraising target from national/international sources for implementing PoWPA; 3.g) Consider strengthen capacity for pressures and threat analysis and explore the possibility of exchanging and harmonising methodologies and mechanisms for this analysis; and 3.h) Explore funding opportunities for protected area design, establishment and effective management to address climate change; noting that effective actions to reduce deforestation could constitute a unique opportunity for biodiversity protection (re CoP decision VIII/30)

- Donor countries are urged to 4.a) Enhance financial support for implementation of new and additional protected areas; 4.b) Support the reporting process of developing countries and countries in transition; 4.c) and d) Support of implementation of the PoWPA by developing countries based on priorities identified in national biodiversity strategies and action plans; and 4.e) Support the next replenishment of the GEF taking into account the PoWPA

- Multilateral donors, NGOs and other funding organizations are urged to 6.a) Make adequate, timely and predictable funding available for the designation and effective management of new protected areas and where applicable the establishment of ecological network that complete representative systems, and for improving management of existing protected areas of all governance types; 6.b) Provide enhanced financial and technical support to endowment funds, national environmental funds and other long-term financing mechanisms; 6.c) Support financial needs assessments, sustainable financial plans and valuation of ecosystem goods and services; 6.d) Support development and implementation of financial strategies and plans for national systems; 6.e) Support projects that demonstrate the role of protected areas in addressing climate change; 6.f) Support proposals on public-private partnerships in the developing countries; 6.g) Support capacity-building for indigenous and local communities to participate in the establishment and management of protected areas to improve their standard of living; 6.h) Supporting the preservation and maintenance of traditional knowledge for the conservation and sustainable use of biodiversity in the management of protected areas.

- Executive Secretary is requested to: 7.a) Promote the importance of financing for protected areas; and 7.c) Compile information assessing the socio-economic values of protected areas.

- GEF is invited to: 9.a) Continue to provide and facilitate easier access to financial resources for protected areas, taking into account PoWPA goals and targets; 9.b) To consider support for proposals that demonstrate the role protected areas play in addressing climate change; 9.c) To ensure that protected areas remain a GEF priority.

6) Encourages developing countries to prioritise PoWPA and mainstream protected areas into relevant sectoral plans.

# Footnotes

The PoWPA is an ambitious, multi-year programme aimed at encouraging signatory states to complete ecologically-representative networks of protected areas. It has 16 major goals and over 90 activities, many with specific target dates. Many elements of PoWPA emerged from The Durban Accord; drawn up by the IUCN World Commission on Protected Areas following the fifth World Parks Congress in Durban, South Africa, in 2003.

Some of these are in the COP 9 Decision IX/18, others have come up in discussion. Other issues could include: reducing illegal activities, better ranger training, addressing perverse incentives, developing protected area standards, etc

Similar issues of transboundary cooperation, resistance from commercial interests and confusion about management models affect the designation of freshwater protected areas, which are also lagging behind terrestrial protected areas. Other biomes and habitats that are currently poorly protected include oases, cave systems, karsts and grasslands.

IUCN’s initiative to “Ensure that protected areas and protected area systems are recognised as an important contribution to climate change adaptation/mitigation strategies for biodiversity and human livelihoods”

www.thegef.org/uploadedFiles/Documents/Council_Documents__(PDF_DOC)/GEF_35/C.35.Inf.2(5).pdf

UNEP-WCMC (2008) State of the world’s protected areas: an annual review of global conservation progress. UNEP-WCMC, Cambridge

Coad,L et al (2008) Progress towards the convention on Biological Diversity terrestrial 2010 and marine 2012 targets for protected area coverage. Parks 17(2)35-42. IUCN, Gland, Switzerland

Some examples are the Sudd-Sahelian swamps, Zambezian flooded grasslands (including the Okavango Delta), Lake Chad flooded savannah and Nile Delta flooded savanna (all in Africa). The Everglades in the USA, the Orinoco and Pantanal wetlands in South America and the marshes of Southern Iraq are examples outside Africa.

UNEP-WCMC(2008) op cit

Laffoley, D et al (2008) Progress with Marine Protected Areas since Durban, and future directions. Parks 17(2) 13-22. IUCN, Gland, Switzerland

www.tbpa.net/tpa_inventory.html

Zbicz, Dorothy C. 2003. Imposing Transboundary Conservation: Cooperation Between Internationally Adjoining Protected Areas, Journal of Sustainable Forestry, 17: 1/2.

Chester, Charles (Lead Author); James Dontje and William C.G. Burns (Topic Editors). 2008. "Transboundary protected areas." In: Encyclopedia of Earth. Eds. Cutler J. Cleveland (Washington, D.C.: Environmental Information Coalition, National Council for Science and the Environment). [First published in the Encyclopedia of Earth November 17, 2006; Last revised September 24, 2008; Retrieved August 26, 2009]. www.eoearth.org/article/Transboundary_protected_areas

www.iucn.org/about/union/commissions/ceesp/topics/governance/icca/ceesp_icca_legislation/

Kothari. (2008) A. Protected areas and people: the future of the past. Parks 17 (2).IUCN, Gland, Switzerland.

Implementation of the CBD in Brazil: Issues on the agenda of COP 9. Ministry of Environment , Brazilian Government

www.protectedareas.org

Economic values of protected areas. Guidelines for protected area Managers, IUCN-WCPA www.iucn.org/themeswcpa/pubs/pdfs/Econbomic_values.pdf.

UNEP/CBD/WG-PA/2/4

UNEP/CBD/WG-PA/2/INF/7

www.testprotectedareas.org

UNEP/CBD/WG-PA/2/INF/8

OECD. 2007. Statistic on Biodiversity-Related AID. OECD Paris. Online at www.oecd.org/dac/stats/crs

ec.europa.eu/environment/nature/nature_conservation/natura_2000_network/manging_natura_2000/exchange_of_good_practice/index.htmal;

www.gbrmpa.gov.au/corp_site/management/zoning/planners_info.html

www.parks.tas.gov.au/publications/tech/management_code/summary.html

The documents can be downloaded from www.iucn.org/about/union/commissions/wcpa/wcpa_puball/wcpa_bpg/index.cfm?

Leverington, F, Hockings, M and Lemos Costa. K (2008). Management Effectiveness Evaluation in Protected areas: Report for the project ‘Global study into management effectiveness evaluation of protected areas’ The University of Queensland, Gatton, IUCN WCPA, TNC, WWF, Australia.

ec.europa.eu/environment/nature/nature_conservation/useful_info/barometer/barometer.htm

# Text boxes

The future of the CBD Programme of Work on Protected Areas

Draft paper for discussion at a meeting on Jeju Island, South Korea, September 2009